## Dashboard
MN8 Energy Style Portfolio Analytics Dashboard
Total Projects |  | Total Capacity (MW) |  | Avg Schedule Variance (Days) |  |  |  | Capacity by Technology (MW)
[8 empty] | Technology | Capacity MW
[8 empty] | Battery Storage | 1524
Projects At Risk |  | Avg Budget Variance % |  | Avg Risk Score |  |  |  | Solar PV | 1361
[8 empty] | Hybrid Solar + Storage | 543
High-Risk Projects | [5 empty] | Root Cause Impact Days
Project ID | Technology | Stage | Delay Days | Budget Var % | Risk Score | Root Cause | Impact Days
MN8-008 | Solar PV | Engineering | 25 | 3.71% | 62.8 | Supply chain | 222
MN8-017 | Battery Storage | Construction | 57 | -8.01% | 62.4 | Weather | 219
MN8-022 | Solar PV | Development | 12 | 5.22% | 62 | Design revision | 153
MN8-010 | Solar PV | Commissioning | 52 | -7.63% | 59.5 | Interconnection delay | 149
MN8-020 | Hybrid Solar + Storage | Engineering | -7 | 9.74% | 58.7 | Permit approval | 131
MN8-018 | Solar PV | Development | -12 | -5.02% | 57.2 | Contractor productivity | 116
MN8-013 | Battery Storage | Commissioning | 21 | 8% | 54.3 | Equipment lead time | 104
MN8-004 | Solar PV | Engineering | -16 | 10.01% | 51.6 | Site access | 96

## Portfolio_Data
project_id | project_name | technology | region | stage | project_manager | epc_vendor | capacity_mw | planned_start | planned_cod | forecast_cod | schedule_variance_days | baseline_budget_usd | actual_spend_usd | budget_variance_pct | percent_complete | risk_score | portfolio_health | commercial_operation_year
MN8-001 | Texas Battery Project 1 | Battery Storage | Texas | Commissioning | L. Kim | BrightPath | 102 | 2025-04-05 | 2025-11-23 | 2025-12-28 | 35 | 90722775 | 75843229 | 3.22 | 81 | 44.9 | Watch | 2025
MN8-002 | Southwest Solar Project 2 | Solar PV | Southwest | Development | D. Singh | SunPeak | 103 | 2025-04-08 | 2026-06-20 | 2026-06-05 | -15 | 96478133 | 11319117 | -6.93 | 12.6 | 38.1 | Healthy | 2026
MN8-003 | Northeast Battery Project 3 | Battery Storage | Northeast | Construction | S. Patel | StorageCore | 154 | 2025-10-09 | 2026-04-10 | 2026-03-28 | -13 | 129749912 | 90008895 | 3.37 | 67.1 | 19.7 | Healthy | 2026
MN8-004 | Southeast Solar Project 4 | Solar PV | Southeast | Engineering | A. Lopez | HelioWorks | 166 | 2025-02-03 | 2026-02-12 | 2026-01-27 | -16 | 152642714 | 64151094 | 10.01 | 38.2 | 51.6 | Watch | 2026
MN8-005 | Northeast Hybrid Project 5 | Hybrid Solar + Storage | Northeast | Engineering | R. Johnson | SunPeak | 131 | 2025-08-18 | 2026-04-18 | 2026-05-21 | 33 | 157583538 | 72202263 | 10.67 | 41.4 | 47.4 | Watch | 2026
MN8-006 | Northeast Battery Project 6 | Battery Storage | Northeast | Operational | A. Lopez | SunPeak | 132 | 2025-10-07 | 2027-03-31 | 2027-04-12 | 12 | 121666858 | 115335692 | -4.03 | 98.8 | 8 | Healthy | 2027
MN8-007 | Midwest Battery Project 7 | Battery Storage | Midwest | Operational | R. Johnson | HelioWorks | 99 | 2025-02-13 | 2026-01-01 | 2025-12-21 | -11 | 80463128 | 86064428 | 6.99 | 100 | 8 | Healthy | 2025
MN8-008 | Midwest Solar Project 8 | Solar PV | Midwest | Engineering | S. Patel | BrightPath | 148 | 2025-02-20 | 2026-07-10 | 2026-08-04 | 25 | 154778612 | 43697017 | 3.71 | 27.2 | 62.8 | Watch | 2026
MN8-009 | Southeast Battery Project 9 | Battery Storage | Southeast | Construction | M. Chen | SunPeak | 109 | 2025-09-08 | 2027-02-20 | 2027-02-21 | 1 | 89147502 | 59799044 | -7.37 | 72.4 | 37.2 | Healthy | 2027
MN8-010 | Texas Solar Project 10 | Solar PV | Texas | Commissioning | D. Singh | HelioWorks | 182 | 2025-05-03 | 2026-02-15 | 2026-04-08 | 52 | 184230490 | 148513330 | -7.63 | 87.3 | 59.5 | At Risk | 2026
MN8-011 | Southwest Solar Project 11 | Solar PV | Southwest | Construction | S. Patel | GridVolt | 244 | 2025-08-05 | 2026-06-16 | 2026-07-07 | 21 | 234940572 | 124406406 | -4.97 | 55.7 | 43.3 | Watch | 2026
MN8-012 | Northeast Battery Project 12 | Battery Storage | Northeast | Engineering | S. Patel | GridVolt | 149 | 2025-10-13 | 2026-10-13 | 2026-10-11 | -2 | 118068735 | 54713612 | -5.9 | 49.2 | 37 | Healthy | 2026
MN8-013 | Texas Battery Project 13 | Battery Storage | Texas | Commissioning | L. Kim | StorageCore | 68 | 2025-03-21 | 2025-12-07 | 2025-12-28 | 21 | 61354008 | 55575569 | 8 | 83.9 | 54.3 | Watch | 2025
MN8-014 | Southwest Battery Project 14 | Battery Storage | Southwest | Construction | A. Lopez | SunPeak | 159 | 2025-09-09 | 2026-12-16 | 2026-11-01 | -45 | 127638574 | 115157270 | 5.47 | 85.5 | 30.1 | Healthy | 2026
MN8-015 | Northeast Battery Project 15 | Battery Storage | Northeast | Commissioning | S. Patel | StorageCore | 127 | 2025-02-10 | 2026-03-19 | 2026-04-15 | 27 | 117934237 | 103470502 | 3.41 | 84.8 | 43.1 | Watch | 2026
MN8-016 | Midwest Solar Project 16 | Solar PV | Midwest | Operational | M. Chen | BrightPath | 125 | 2025-09-04 | 2027-01-17 | 2026-12-30 | -18 | 119466162 | 113848694 | -4.67 | 100 | 8 | Healthy | 2026
MN8-017 | Southeast Battery Project 17 | Battery Storage | Southeast | Construction | A. Lopez | BrightPath | 81 | 2025-09-25 | 2026-12-20 | 2027-02-15 | 57 | 65237269 | 43320275 | -8.01 | 72.2 | 62.4 | At Risk | 2027
MN8-018 | Texas Solar Project 18 | Solar PV | Texas | Development | S. Patel | BrightPath | 172 | 2025-05-08 | 2025-12-03 | 2025-11-21 | -12 | 161216237 | 9217346 | -5.02 | 6 | 57.2 | Watch | 2025
MN8-019 | Texas Hybrid Project 19 | Hybrid Solar + Storage | Texas | Commissioning | S. Patel | StorageCore | 137 | 2025-09-25 | 2026-05-27 | 2026-05-08 | -19 | 177789618 | 168317789 | 10.34 | 85.8 | 48.1 | Healthy | 2026
MN8-020 | Southeast Hybrid Project 20 | Hybrid Solar + Storage | Southeast | Engineering | L. Kim | GridVolt | 275 | 2025-07-07 | 2026-10-06 | 2026-09-29 | -7 | 354748903 | 162165653 | 9.74 | 41.7 | 58.7 | Watch | 2026
MN8-021 | Southwest Battery Project 21 | Battery Storage | Southwest | Operational | A. Lopez | GridVolt | 135 | 2025-08-17 | 2026-10-02 | 2026-10-16 | 14 | 111055734 | 115127357 | 4.12 | 99.6 | 8 | Healthy | 2026
MN8-022 | Midwest Solar Project 22 | Solar PV | Midwest | Development | A. Lopez | SunPeak | 221 | 2025-04-19 | 2026-02-05 | 2026-02-17 | 12 | 199306510 | 15805677 | 5.22 | 7.5 | 62 | Watch | 2026
MN8-023 | Texas Battery Project 23 | Battery Storage | Texas | Engineering | S. Patel | HelioWorks | 48 | 2025-06-03 | 2026-08-20 | 2026-07-15 | -36 | 42531382 | 15445262 | 4.47 | 34.8 | 43.7 | Healthy | 2026
MN8-024 | Southeast Battery Project 24 | Battery Storage | Southeast | Construction | R. Johnson | GridVolt | 161 | 2025-04-26 | 2026-06-22 | 2026-06-10 | -12 | 133229382 | 120190502 | 3.89 | 86.8 | 35.7 | Healthy | 2026

## Monthly_Data
project_id | month | planned_progress_pct | actual_progress_pct | monthly_capex_usd | cumulative_spend_usd | performance_ratio | irradiance_kwh_m2 | safety_incidents | change_orders
MN8-001 | 2025-10-01 | 59.9 | 55.5 | 11805639 | 66841982 | 0.932 |  | 0 | 2
MN8-001 | 2025-11-01 | 74.2 | 67.3 | 13157202 | 69928167 | 0.954 |  | 0 | 2
MN8-001 | 2025-12-01 | 78.2 | 78.2 | 20429811 | 72900501 | 0.894 |  | 0 | 2
MN8-001 | 2026-01-01 | 92.4 | 90 | 9029585 | 75839508 | 0.959 |  | 0 | 0
MN8-001 | 2026-02-01 | 100 | 100 | 12995904 | 72670475 | 0.945 |  | 1 | 1
MN8-001 | 2026-03-01 | 100 | 100 | 15143390 | 75843229 | 0.932 |  | 0 | 1
MN8-002 | 2025-10-01 | 3.2 | 7.7 | 15526516 | 11212081 | 0.824 | 5.91 | 0 | 0
MN8-002 | 2025-11-01 | 16.1 | 16.5 | 10082938 | 11182061 | 0.882 | 4.83 | 0 | 0
MN8-002 | 2025-12-01 | 30.4 | 27.1 | 19715167 | 11319117 | 0.852 | 5.14 | 0 | 0
MN8-002 | 2026-01-01 | 35.6 | 39.6 | 8447476 | 11319117 | 0.89 | 6.22 | 0 | 0
MN8-002 | 2026-02-01 | 50.2 | 45.9 | 18655613 | 10825506 | 0.905 | 6.34 | 0 | 1
MN8-002 | 2026-03-01 | 47.8 | 49.5 | 13763774 | 11319117 | 0.792 | 4.54 | 0 | 0
MN8-003 | 2025-10-01 | 44.2 | 43 | 14557981 | 84397184 | 0.912 |  | 0 | 1
MN8-003 | 2025-11-01 | 45.2 | 45.4 | 24346704 | 88695459 | 0.949 |  | 0 | 0
MN8-003 | 2025-12-01 | 52.3 | 49.7 | 31144958 | 89541897 | 0.911 |  | 0 | 0
MN8-003 | 2026-01-01 | 65.8 | 58.5 | 19161957 | 90008895 | 0.952 |  | 0 | 0
MN8-003 | 2026-02-01 | 61.6 | 62.4 | 29082909 | 83080492 | 0.945 |  | 0 | 0
MN8-003 | 2026-03-01 | 76 | 72.8 | 29787812 | 90008895 | 0.944 |  | 0 | 0
MN8-004 | 2025-10-01 | 21 | 15.9 | 21390422 | 64151094 | 0.893 | 5.44 | 0 | 1
MN8-004 | 2025-11-01 | 24.7 | 18 | 25574075 | 64151094 | 0.828 | 6.8 | 0 | 0
MN8-004 | 2025-12-01 | 36.2 | 28.9 | 36904102 | 63801273 | 0.866 | 5.5 | 0 | 0
MN8-004 | 2026-01-01 | 41.8 | 37 | 32858355 | 64151094 | 0.801 | 5.63 | 0 | 0
MN8-004 | 2026-02-01 | 40.6 | 44.1 | 16357999 | 64151094 | 0.864 | 4.49 | 0 | 1
MN8-004 | 2026-03-01 | 56.7 | 51 | 30687348 | 59697426 | 0.8 | 7.06 | 0 | 0
MN8-005 | 2025-10-01 | 16.8 | 20.7 | 33542888 | 71667429 | 0.861 | 6.54 | 0 | 0
MN8-005 | 2025-11-01 | 29.6 | 28.5 | 14610706 | 67541342 | 0.824 | 5.82 | 0 | 1
MN8-005 | 2025-12-01 | 43.1 | 36.8 | 19004465 | 72202263 | 0.811 | 6.72 | 0 | 1
MN8-005 | 2026-01-01 | 51.2 | 43.3 | 15070149 | 71624721 | 0.926 | 5.46 | 0 | 1
MN8-005 | 2026-02-01 | 60.9 | 54.2 | 14325562 | 69063285 | 0.924 | 6.49 | 0 | 1
MN8-005 | 2026-03-01 | 62.7 | 65.3 | 25310501 | 69742750 | 0.88 | 4.22 | 2 | 3
MN8-006 | 2025-10-01 | 75.2 | 78 | 28610513 | 113269689 | 0.956 |  | 0 | 1
MN8-006 | 2025-11-01 | 95.2 | 88.1 | 27700784 | 106786829 | 0.882 |  | 0 | 1
MN8-006 | 2025-12-01 | 100 | 100 | 29806644 | 115335692 | 0.947 |  | 0 | 0
MN8-006 | 2026-01-01 | 95.7 | 100 | 27673581 | 115335692 | 0.96 |  | 2 | 1
MN8-006 | 2026-02-01 | 96.7 | 100 | 29484970 | 115197601 | 0.898 |  | 0 | 1
MN8-006 | 2026-03-01 | 96.5 | 100 | 23756938 | 113910143 | 0.942 |  | 0 | 1
MN8-007 | 2025-10-01 | 78.1 | 82.7 | 16832045 | 80539903 | 0.936 |  | 0 | 0
MN8-007 | 2025-11-01 | 86 | 86.5 | 14616364 | 83567847 | 0.915 |  | 1 | 0
MN8-007 | 2025-12-01 | 96.8 | 93.7 | 18270008 | 86064428 | 0.892 |  | 1 | 0
MN8-007 | 2026-01-01 | 100 | 100 | 19848008 | 84690870 | 0.906 |  | 0 | 0
MN8-007 | 2026-02-01 | 99.5 | 100 | 18731661 | 84482135 | 0.933 |  | 0 | 0
MN8-007 | 2026-03-01 | 97.2 | 100 | 10441302 | 81159734 | 0.887 |  | 0 | 0
MN8-008 | 2025-10-01 | 21.5 | 16.1 | 29095809 | 40665697 | 0.895 | 6.87 | 0 | 0
MN8-008 | 2025-11-01 | 31.7 | 27 | 17658202 | 41390488 | 0.834 | 5.61 | 0 | 0
MN8-008 | 2025-12-01 | 43.8 | 37.1 | 26097672 | 43223986 | 0.803 | 5.5 | 0 | 0
MN8-008 | 2026-01-01 | 41 | 41.1 | 13415983 | 42030862 | 0.815 | 5.15 | 0 | 1
MN8-008 | 2026-02-01 | 54.3 | 52.8 | 15140451 | 43252350 | 0.86 | 6.36 | 0 | 0
MN8-008 | 2026-03-01 | 60.7 | 61 | 29560580 | 43443626 | 0.833 | 7.06 | 0 | 0
MN8-009 | 2025-10-01 | 59.4 | 60.7 | 10004929 | 48169563 | 0.886 |  | 0 | 0
MN8-009 | 2025-11-01 | 68.3 | 71.8 | 13340264 | 59799044 | 0.949 |  | 1 | 0
MN8-009 | 2025-12-01 | 81 | 78.8 | 15921932 | 57191643 | 0.942 |  | 0 | 0
MN8-009 | 2026-01-01 | 88.6 | 87 | 11030662 | 55907848 | 0.929 |  | 0 | 1
MN8-009 | 2026-02-01 | 95.2 | 99.5 | 12430197 | 56060043 | 0.885 |  | 2 | 0
MN8-009 | 2026-03-01 | 98.3 | 100 | 17554669 | 59799044 | 0.928 |  | 0 | 0
MN8-010 | 2025-10-01 | 72.9 | 75.6 | 17394314 | 141014179 | 0.859 | 6.64 | 0 | 1
MN8-010 | 2025-11-01 | 77.8 | 80.6 | 20396336 | 148513330 | 0.87 | 5.72 | 0 | 1
MN8-010 | 2025-12-01 | 86.2 | 86.3 | 29559161 | 142450886 | 0.88 | 5.66 | 0 | 1
MN8-010 | 2026-01-01 | 97.9 | 95.9 | 43185841 | 148513330 | 0.804 | 6.93 | 0 | 0
MN8-010 | 2026-02-01 | 100 | 100 | 42799586 | 148513330 | 0.808 | 5.1 | 0 | 1
MN8-010 | 2026-03-01 | 100 | 100 | 38763897 | 148513330 | 0.831 | 6.58 | 0 | 1
MN8-011 | 2025-10-01 | 52.1 | 47.8 | 47772680 | 124406406 | 0.873 | 5.77 | 0 | 0
MN8-011 | 2025-11-01 | 58.9 | 52.1 | 42422115 | 120936796 | 0.845 | 6.95 | 0 | 1
MN8-011 | 2025-12-01 | 66.3 | 60 | 56077115 | 123593698 | 0.874 | 6.88 | 0 | 0
MN8-011 | 2026-01-01 | 71.9 | 69 | 36185965 | 124406406 | 0.902 | 6.88 | 0 | 0
MN8-011 | 2026-02-01 | 87.7 | 87.5 | 21722669 | 119874982 | 0.886 | 4.21 | 0 | 0
MN8-011 | 2026-03-01 | 100 | 97.4 | 33140169 | 120065110 | 0.879 | 5.51 | 0 | 0
MN8-012 | 2025-10-01 | 41.4 | 41.7 | 21263950 | 54713612 | 0.881 |  | 0 | 0
MN8-012 | 2025-11-01 | 50.2 | 53.3 | 17998086 | 50943596 | 0.96 |  | 0 | 1
MN8-012 | 2025-12-01 | 62.8 | 56.2 | 13875824 | 51692841 | 0.883 |  | 0 | 1
MN8-012 | 2026-01-01 | 67.7 | 62.7 | 18758934 | 54066390 | 0.915 |  | 0 | 1
MN8-012 | 2026-02-01 | 76.2 | 68.9 | 17185088 | 52262268 | 0.932 |  | 0 | 0
MN8-012 | 2026-03-01 | 78.2 | 73.8 | 22805447 | 50529251 | 0.898 |  | 0 | 1
MN8-013 | 2025-10-01 | 78.6 | 80.5 | 6129689 | 40921503 | 0.938 |  | 1 | 1
MN8-013 | 2025-11-01 | 89 | 85.3 | 7208935 | 48130439 | 0.952 |  | 0 | 0
MN8-013 | 2025-12-01 | 93.7 | 87.1 | 13471740 | 53599094 | 0.901 |  | 0 | 1
MN8-013 | 2026-01-01 | 100 | 97.9 | 9299342 | 55117967 | 0.915 |  | 0 | 2
MN8-013 | 2026-02-01 | 100 | 100 | 9460926 | 51291860 | 0.901 |  | 0 | 1
MN8-013 | 2026-03-01 | 96.8 | 100 | 13650553 | 55575569 | 0.922 |  | 0 | 0
MN8-014 | 2025-10-01 | 73.5 | 71.3 | 24494276 | 115157270 | 0.897 |  | 0 | 0
MN8-014 | 2025-11-01 | 90.5 | 84.2 | 23345374 | 114934693 | 0.933 |  | 0 | 2
MN8-014 | 2025-12-01 | 88.4 | 92.8 | 14173910 | 115157270 | 0.887 |  | 0 | 0
MN8-014 | 2026-01-01 | 93 | 94.3 | 18202808 | 115157270 | 0.904 |  | 0 | 0
MN8-014 | 2026-02-01 | 97.8 | 100 | 11299910 | 109870898 | 0.928 |  | 0 | 0
MN8-014 | 2026-03-01 | 99.3 | 100 | 27036237 | 107540512 | 0.886 |  | 0 | 0
MN8-015 | 2025-10-01 | 67.6 | 63.6 | 15177058 | 88507310 | 0.909 |  | 0 | 2
MN8-015 | 2025-11-01 | 77.6 | 70.3 | 18594412 | 97683115 | 0.923 |  | 1 | 1
MN8-015 | 2025-12-01 | 90.3 | 84.2 | 14735254 | 101776198 | 0.898 |  | 2 | 2
MN8-015 | 2026-01-01 | 95.7 | 91.5 | 28014262 | 97621811 | 0.925 |  | 1 | 0
MN8-015 | 2026-02-01 | 100 | 100 | 28388078 | 101571596 | 0.949 |  | 1 | 0
MN8-015 | 2026-03-01 | 95.5 | 100 | 21547959 | 98286749 | 0.89 |  | 0 | 1
MN8-016 | 2025-10-01 | 89.3 | 84.1 | 16302203 | 105239857 | 0.896 | 5.99 | 0 | 0
MN8-016 | 2025-11-01 | 85.8 | 90.5 | 27371722 | 112569243 | 0.903 | 6.52 | 2 | 0
MN8-016 | 2025-12-01 | 100 | 99.7 | 27351322 | 113848694 | 0.882 | 5.41 | 0 | 1
MN8-016 | 2026-01-01 | 96.1 | 99.7 | 17016405 | 108992030 | 0.826 | 4.88 | 0 | 0
MN8-016 | 2026-02-01 | 100 | 100 | 14301173 | 113848694 | 0.884 | 4.46 | 0 | 1
MN8-016 | 2026-03-01 | 100 | 100 | 22169164 | 107212956 | 0.909 | 4.87 | 1 | 1
MN8-017 | 2025-10-01 | 46.2 | 48.8 | 13912766 | 41826431 | 0.885 |  | 1 | 1
MN8-017 | 2025-11-01 | 65.9 | 57.9 | 7327181 | 42086144 | 0.941 |  | 0 | 0
MN8-017 | 2025-12-01 | 67.9 | 65.9 | 11883403 | 43121487 | 0.887 |  | 1 | 0
MN8-017 | 2026-01-01 | 74.9 | 68.4 | 15827121 | 43320275 | 0.945 |  | 0 | 1
MN8-017 | 2026-02-01 | 66.3 | 67.9 | 13302098 | 42647245 | 0.886 |  | 0 | 1
MN8-017 | 2026-03-01 | 74.6 | 68.6 | 10820107 | 42561142 | 0.927 |  | 1 | 0
MN8-018 | 2025-10-01 | 10.6 | 7 | 36289284 | 9217346 | 0.875 | 6.63 | 0 | 1
MN8-018 | 2025-11-01 | 21.8 | 17 | 17696306 | 9217346 | 0.895 | 4.28 | 1 | 0
MN8-018 | 2025-12-01 | 27.9 | 22.3 | 35793610 | 9088034 | 0.791 | 5.03 | 0 | 3
MN8-018 | 2026-01-01 | 31.3 | 32.9 | 30470022 | 9126998 | 0.884 | 4.51 | 0 | 0
MN8-018 | 2026-02-01 | 55 | 47.9 | 16189059 | 9217346 | 0.873 | 4.4 | 0 | 1
MN8-018 | 2026-03-01 | 51.7 | 49.2 | 22728347 | 9217346 | 0.795 | 6.73 | 2 | 2
MN8-019 | 2025-10-01 | 70.9 | 65.8 | 35062939 | 141527569 | 0.843 | 6.79 | 0 | 0
MN8-019 | 2025-11-01 | 71.7 | 66.4 | 35370718 | 159683095 | 0.82 | 5.91 | 0 | 0
MN8-019 | 2025-12-01 | 85 | 77.7 | 27252995 | 168317789 | 0.858 | 4.77 | 2 | 0
MN8-019 | 2026-01-01 | 84.3 | 86.3 | 21130435 | 155533620 | 0.888 | 5.03 | 1 | 0
MN8-019 | 2026-02-01 | 100 | 99 | 37659452 | 168317789 | 0.901 | 5.75 | 0 | 0
MN8-019 | 2026-03-01 | 100 | 100 | 38418478 | 165388707 | 0.824 | 4.35 | 0 | 0
MN8-020 | 2025-10-01 | 28.9 | 23.5 | 47912503 | 158789140 | 0.811 | 4.2 | 0 | 0
MN8-020 | 2025-11-01 | 32.8 | 34 | 70653086 | 162165653 | 0.904 | 4.11 | 0 | 0
MN8-020 | 2025-12-01 | 50.4 | 46.3 | 62651535 | 149398385 | 0.849 | 5.45 | 0 | 0
MN8-020 | 2026-01-01 | 46.8 | 50.8 | 53030425 | 151990253 | 0.878 | 5.93 | 1 | 0
MN8-020 | 2026-02-01 | 61.3 | 57.1 | 31429934 | 162165653 | 0.816 | 5.52 | 0 | 1
MN8-020 | 2026-03-01 | 70.6 | 65.1 | 49632339 | 162165653 | 0.82 | 6.51 | 0 | 1
MN8-021 | 2025-10-01 | 78.9 | 83.1 | 13828350 | 101428114 | 0.95 |  | 0 | 3
MN8-021 | 2025-11-01 | 88 | 90.6 | 23871402 | 115127357 | 0.92 |  | 0 | 1
MN8-021 | 2025-12-01 | 97.8 | 94 | 10590986 | 106375931 | 0.901 |  | 0 | 1
MN8-021 | 2026-01-01 | 100 | 100 | 17130224 | 111094624 | 0.91 |  | 2 | 0
MN8-021 | 2026-02-01 | 100 | 100 | 18262541 | 115127357 | 0.952 |  | 0 | 0
MN8-021 | 2026-03-01 | 100 | 100 | 13153852 | 115127357 | 0.931 |  | 0 | 0
MN8-022 | 2025-10-01 | 7.9 | 6.5 | 24821336 | 15805677 | 0.843 | 5.69 | 0 | 1
MN8-022 | 2025-11-01 | 11.5 | 11.4 | 48810574 | 15071619 | 0.869 | 5.14 | 0 | 0
MN8-022 | 2025-12-01 | 15.6 | 19.6 | 22247852 | 15609222 | 0.83 | 6.6 | 0 | 0
MN8-022 | 2026-01-01 | 32.3 | 28.2 | 22157632 | 14885636 | 0.794 | 6.34 | 0 | 0
MN8-022 | 2026-02-01 | 46.4 | 40.1 | 23446458 | 14771188 | 0.822 | 4.37 | 0 | 2
MN8-022 | 2026-03-01 | 44.6 | 48 | 31629911 | 15805677 | 0.828 | 5.67 | 0 | 0
MN8-023 | 2025-10-01 | 11 | 4.8 | 6767734 | 15244898 | 0.919 |  | 0 | 0
MN8-023 | 2025-11-01 | 9.4 | 10.4 | 8539456 | 14614939 | 0.934 |  | 1 | 0
MN8-023 | 2025-12-01 | 20.1 | 22.8 | 8454005 | 15445262 | 0.956 |  | 0 | 0
MN8-023 | 2026-01-01 | 37.9 | 31.6 | 7589085 | 14270655 | 0.954 |  | 0 | 1
MN8-023 | 2026-02-01 | 38.4 | 34.9 | 4299873 | 15445262 | 0.96 |  | 0 | 3
MN8-023 | 2026-03-01 | 52.9 | 46.6 | 9090271 | 15348144 | 0.939 |  | 1 | 0
MN8-024 | 2025-10-01 | 78.5 | 77.8 | 29262373 | 112453500 | 0.924 |  | 0 | 0
MN8-024 | 2025-11-01 | 86.8 | 86.6 | 26545226 | 116646391 | 0.916 |  | 0 | 0
MN8-024 | 2025-12-01 | 96.9 | 93.2 | 24858168 | 117817247 | 0.91 |  | 1 | 0
MN8-024 | 2026-01-01 | 94.9 | 99.6 | 18679821 | 116515729 | 0.912 |  | 0 | 0
MN8-024 | 2026-02-01 | 100 | 100 | 32319754 | 110860142 | 0.896 |  | 0 | 1
MN8-024 | 2026-03-01 | 98.2 | 100 | 31687155 | 111516926 | 0.955 |  | 0 | 0

## Issue_Log
issue_id | project_id | opened_date | closed_date | root_cause | severity | status | impact_days | impact_cost_usd | owner_function | requires_exec_escalation
ISS-0001 | MN8-001 | 2025-10-14 | 2025-11-19 | Interconnection delay | Medium | Closed | 29 | 93509 | Engineering | No
ISS-0002 | MN8-001 | 2025-08-02 | 2025-09-21 | Design revision | High | Closed | 45 | 224050 | Procurement | Yes
ISS-0003 | MN8-001 | 2025-09-07 | 2025-09-27 | Supply chain | Low | Closed | 1 | 29229 | Project Controls | No
ISS-0004 | MN8-001 | 2025-09-28 | 2025-10-15 | Weather | Low | Open | 5 | 74148 | Construction | No
ISS-0005 | MN8-001 | 2025-08-02 | 2025-09-13 | Supply chain | High | Closed | 31 | 222702 | Development | Yes
ISS-0006 | MN8-001 | 2025-09-06 | 2025-10-17 | Supply chain | High | Closed | 22 | 173235 | Construction | Yes
ISS-0007 | MN8-002 | 2025-08-06 | 2025-09-01 | Permit approval | Medium | Closed | 13 | 91238 | Construction | No
ISS-0008 | MN8-002 | 2025-11-10 | 2025-12-13 | Equipment lead time | Medium | Closed | 21 | 87279 | Development | No
ISS-0009 | MN8-002 | 2025-09-10 | 2025-10-09 | Design revision | Medium | Closed | 15 | 92484 | Engineering | No
ISS-0010 | MN8-003 | 2025-10-02 | 2025-10-21 | Contractor productivity | Medium | Closed | 18 | 58581 | Construction | No
ISS-0011 | MN8-003 | 2025-09-02 | 2025-10-23 | Contractor productivity | High | Open | 38 | 141423 | Engineering | Yes
ISS-0012 | MN8-003 | 2025-08-22 | 2025-08-29 | Site access | Low | Open | 9 | 35589 | Construction | No
ISS-0013 | MN8-004 | 2025-09-19 | 2025-11-11 | Interconnection delay | High | Closed | 32 | 168984 | Development | Yes
ISS-0014 | MN8-004 | 2025-12-17 | 2026-01-06 | Interconnection delay | Medium | Closed | 9 | 43627 | Procurement | No
ISS-0015 | MN8-004 | 2025-09-09 | 2025-10-10 | Permit approval | Medium | Closed | 20 | 10967 | Procurement | No
ISS-0016 | MN8-005 | 2025-08-01 | 2025-09-19 | Weather | High | Closed | 36 | 253053 | Development | Yes
ISS-0017 | MN8-005 | 2025-09-17 | 2025-09-19 | Quality rework | Low | Closed | 6 | 80677 | Procurement | No
ISS-0018 | MN8-005 | 2025-10-10 | 2025-11-10 | Site access | High | Closed | 30 | 179906 | Development | Yes
ISS-0019 | MN8-005 | 2025-12-01 | 2026-01-06 | Design revision | Medium | Closed | 7 | 5397 | Development | No
ISS-0020 | MN8-005 | 2025-09-09 | 2025-09-21 | Equipment lead time | Medium | Closed | 19 | 119682 | Engineering | No
ISS-0021 | MN8-005 | 2025-10-20 | 2025-11-10 | Supply chain | Low | Closed | 1 | 0 | Procurement | No
ISS-0022 | MN8-006 | 2025-10-17 | 2025-11-23 | Permit approval | Medium | Closed | 18 | 11051 | Engineering | No
ISS-0023 | MN8-006 | 2025-10-02 | 2025-10-17 | Interconnection delay | Medium | Closed | 24 | 5327 | Project Controls | No
ISS-0024 | MN8-006 | 2025-11-18 | 2025-11-23 | Design revision | Low | Closed | 0 | 108598 | Development | No
ISS-0025 | MN8-007 | 2025-09-18 | 2025-09-30 | Interconnection delay | Low | Closed | 6 | 0 | Procurement | No
ISS-0026 | MN8-007 | 2025-09-02 | 2025-09-28 | Contractor productivity | Low | Closed | 16 | 54176 | Engineering | No
ISS-0027 | MN8-007 | 2025-09-22 | 2025-10-07 | Site access | Low | Closed | 0 | 0 | Development | No
ISS-0028 | MN8-008 | 2025-12-24 | 2026-01-11 | Site access | Medium | Closed | 11 | 147708 | Project Controls | No
ISS-0029 | MN8-008 | 2025-09-14 | 2025-11-01 | Site access | High | Closed | 23 | 135419 | Procurement | Yes
ISS-0030 | MN8-008 | 2025-09-09 | 2025-10-17 | Supply chain | Medium | Closed | 6 | 73657 | Engineering | No
ISS-0031 | MN8-008 | 2025-11-08 | 2025-12-11 | Weather | Low | Closed | 2 | 74130 | Construction | No
ISS-0032 | MN8-009 | 2025-09-08 | 2025-10-13 | Equipment lead time | High | Closed | 20 | 165762 | Project Controls | No
ISS-0033 | MN8-009 | 2025-08-25 | 2025-09-24 | Weather | Low | Closed | 5 | 119370 | Development | No
ISS-0034 | MN8-009 | 2025-12-11 | 2026-01-31 | Weather | High | Open | 29 | 166090 | Engineering | Yes
ISS-0035 | MN8-009 | 2025-12-09 | 2025-12-28 | Site access | Low | Closed | 3 | 46865 | Development | No
ISS-0036 | MN8-010 | 2025-12-04 | 2026-01-30 | Weather | High | Closed | 20 | 139961 | Development | No
ISS-0037 | MN8-010 | 2025-12-26 | 2026-01-05 | Permit approval | Low | Closed | 3 | 18923 | Project Controls | No
ISS-0038 | MN8-010 | 2025-10-20 | 2025-11-14 | Equipment lead time | Low | Closed | 0 | 0 | Engineering | No
ISS-0039 | MN8-010 | 2025-11-23 | 2026-01-31 | Supply chain | High | Closed | 20 | 217635 | Project Controls | No
ISS-0040 | MN8-010 | 2025-09-20 | 2025-10-22 | Permit approval | Medium | Closed | 14 | 69930 | Construction | No
ISS-0041 | MN8-011 | 2025-10-07 | 2025-10-25 | Contractor productivity | Low | Closed | 0 | 54890 | Development | No
ISS-0042 | MN8-011 | 2025-11-15 | 2025-11-17 | Contractor productivity | Low | Closed | 15 | 63761 | Development | No
ISS-0043 | MN8-011 | 2025-09-22 | 2025-11-26 | Weather | High | Closed | 29 | 163738 | Development | Yes
ISS-0044 | MN8-011 | 2025-08-27 | 2025-09-23 | Design revision | Medium | Open | 9 | 114148 | Project Controls | No
ISS-0045 | MN8-011 | 2025-09-05 | 2025-09-30 | Design revision | Low | Closed | 5 | 0 | Project Controls | No
ISS-0046 | MN8-011 | 2025-08-15 | 2025-10-12 | Quality rework | Medium | Closed | 19 | 0 | Development | No
ISS-0047 | MN8-012 | 2025-11-13 | 2025-12-28 | Permit approval | Medium | Closed | 16 | 70466 | Engineering | No
ISS-0048 | MN8-012 | 2025-08-25 | 2025-09-28 | Site access | High | Closed | 20 | 166265 | Project Controls | No
ISS-0049 | MN8-013 | 2025-11-02 | 2025-12-03 | Supply chain | Medium | Closed | 5 | 0 | Engineering | No
ISS-0050 | MN8-013 | 2025-12-18 | 2026-02-04 | Weather | High | Closed | 29 | 136371 | Construction | Yes
ISS-0051 | MN8-013 | 2025-12-14 | 2026-01-22 | Design revision | Medium | Open | 9 | 0 | Development | No
ISS-0052 | MN8-013 | 2025-11-15 | 2025-12-15 | Weather | Low | Closed | 13 | 0 | Project Controls | No
ISS-0053 | MN8-013 | 2025-12-16 | 2025-12-28 | Site access | Low | Closed | 0 | 88777 | Procurement | No
ISS-0054 | MN8-013 | 2025-09-09 | 2025-10-10 | Weather | Medium | Closed | 2 | 109695 | Development | No
ISS-0055 | MN8-014 | 2025-11-23 | 2025-12-05 | Interconnection delay | Low | Closed | 2 | 0 | Project Controls | No
ISS-0056 | MN8-014 | 2025-12-15 | 2026-01-08 | Interconnection delay | Medium | Closed | 15 | 41743 | Project Controls | No
ISS-0057 | MN8-014 | 2025-12-23 | 2026-01-24 | Supply chain | Medium | Closed | 7 | 957 | Development | No
ISS-0058 | MN8-014 | 2025-10-10 | 2025-11-06 | Equipment lead time | Low | Closed | 8 | 117991 | Construction | No
ISS-0059 | MN8-015 | 2025-12-08 | 2025-12-26 | Contractor productivity | Medium | Closed | 11 | 17345 | Procurement | No
ISS-0060 | MN8-015 | 2025-10-22 | 2025-10-24 | Weather | Low | Closed | 8 | 49162 | Construction | No
ISS-0061 | MN8-015 | 2025-09-20 | 2025-11-01 | Supply chain | High | Closed | 9 | 155419 | Construction | No
ISS-0062 | MN8-016 | 2025-08-21 | 2025-09-25 | Contractor productivity | Medium | Closed | 2 | 116483 | Construction | No
ISS-0063 | MN8-016 | 2025-10-07 | 2025-10-29 | Permit approval | Low | Closed | 12 | 9494 | Procurement | No
ISS-0064 | MN8-016 | 2025-11-09 | 2025-12-06 | Supply chain | Medium | Open | 18 | 11138 | Construction | No
ISS-0065 | MN8-016 | 2025-10-08 | 2025-10-22 | Interconnection delay | Medium | Closed | 12 | 52468 | Engineering | No
ISS-0066 | MN8-017 | 2025-09-08 | 2025-10-15 | Supply chain | Medium | Closed | 0 | 49977 | Engineering | No
ISS-0067 | MN8-017 | 2025-10-06 | 2025-10-15 | Contractor productivity | Low | Closed | 0 | 27820 | Engineering | No
ISS-0068 | MN8-017 | 2025-10-19 | 2025-12-08 | Supply chain | High | Closed | 35 | 129563 | Construction | Yes
ISS-0069 | MN8-018 | 2025-08-19 | 2025-09-18 | Weather | Medium | Closed | 10 | 66056 | Project Controls | No
ISS-0070 | MN8-018 | 2025-12-26 | 2026-01-28 | Interconnection delay | Medium | Closed | 17 | 92890 | Development | No
ISS-0071 | MN8-018 | 2025-11-22 | 2025-11-24 | Supply chain | Low | Closed | 4 | 0 | Development | No
ISS-0072 | MN8-018 | 2025-11-27 | 2025-12-12 | Design revision | Low | Closed | 4 | 58927 | Construction | No
ISS-0073 | MN8-018 | 2025-11-23 | 2025-12-24 | Quality rework | Medium | Closed | 14 | 105688 | Project Controls | No
ISS-0074 | MN8-019 | 2025-10-20 | 2025-12-19 | Supply chain | High | Open | 18 | 136277 | Development | No
ISS-0075 | MN8-019 | 2025-12-09 | 2026-01-22 | Supply chain | Medium | Closed | 8 | 22889 | Project Controls | No
ISS-0076 | MN8-019 | 2025-11-08 | 2025-12-01 | Supply chain | Low | Closed | 13 | 47353 | Development | No
ISS-0077 | MN8-019 | 2025-08-16 | 2025-09-26 | Design revision | Medium | Open | 7 | 6019 | Project Controls | No
ISS-0078 | MN8-020 | 2025-10-11 | 2025-11-27 | Weather | Medium | Closed | 11 | 64717 | Development | No
ISS-0079 | MN8-020 | 2025-08-17 | 2025-09-03 | Design revision | Low | Open | 9 | 1115 | Engineering | No
ISS-0080 | MN8-020 | 2025-12-25 | 2026-02-01 | Permit approval | Medium | Closed | 12 | 21984 | Construction | No
ISS-0081 | MN8-021 | 2025-08-03 | 2025-09-18 | Design revision | Medium | Closed | 25 | 103561 | Construction | No
ISS-0082 | MN8-021 | 2025-12-12 | 2026-01-04 | Design revision | Low | Closed | 0 | 31164 | Development | No
ISS-0083 | MN8-021 | 2025-12-11 | 2026-02-02 | Equipment lead time | High | Closed | 26 | 153235 | Construction | Yes
ISS-0084 | MN8-022 | 2025-08-24 | 2025-08-29 | Equipment lead time | Low | Closed | 0 | 58842 | Engineering | No
ISS-0085 | MN8-022 | 2025-09-07 | 2025-10-19 | Supply chain | High | Closed | 22 | 189476 | Construction | Yes
ISS-0086 | MN8-022 | 2025-12-20 | 2026-01-26 | Equipment lead time | Medium | Closed | 10 | 69883 | Engineering | No
ISS-0087 | MN8-022 | 2025-10-06 | 2025-10-31 | Supply chain | Low | Closed | 2 | 28605 | Development | No
ISS-0088 | MN8-023 | 2025-08-18 | 2025-08-20 | Interconnection delay | Low | Closed | 3 | 87331 | Project Controls | No
ISS-0089 | MN8-023 | 2025-08-28 | 2025-10-03 | Design revision | Medium | Closed | 18 | 99830 | Procurement | No
ISS-0090 | MN8-024 | 2025-09-02 | 2025-10-15 | Weather | Medium | Closed | 20 | 34027 | Construction | No
ISS-0091 | MN8-024 | 2025-11-03 | 2025-11-23 | Interconnection delay | Low | Closed | 0 | 0 | Engineering | No
ISS-0092 | MN8-024 | 2025-10-03 | 2025-11-23 | Permit approval | High | Open | 23 | 192302 | Engineering | Yes
ISS-0093 | MN8-024 | 2025-12-26 | 2026-01-26 | Contractor productivity | Medium | Closed | 16 | 50911 | Development | No